## Details
Name | PPM
Author | Deepti Sharma
Approved By | Praveen Ramachandra
Document Version | V1.2

## customer
Field Label | Data Type | values
Customer Name | Name
Customer Owner | Lookup(User)
Customer Site | Text(80)
Customer Source | Picklist | Web
Phone Inquiry
Partner Referral
Purchased List
Other
Annual Revenue | Currency(18, 0)
Billing Address | Address
Created By | Lookup(User)
Description | Long Text Area(32000)
Employees | Number(8, 0)
Fax | Fax
Industry | Picklist | Agriculture
Apparel
Banking
Biotechnology
Chemicals
Communications
Construction
Consulting
Education
Electronics
Energy
Engineering
Entertainment
Environmental
Finance
Food & Beverage
Government
Healthcare
Hospitality
Insurance
Machinery
Manufacturing
Media
Not For Profit
Recreation
Retail
Shipping
Technology
Telecommunications
Transportation
Utilities
Other
Last Modified By | Lookup(User)
Ownership | Picklist | Public
Private
Subsidiary
Other
Parent Customer | Hierarchy
Phone | Phone
Rating | Picklist | hot
warm
cold
Address | Address
Type | Picklist | Prospect
Customer - Direct
Customer - Channel
Channel Partner / Reseller
Installation Partner
Technology Partner
Other
Website | URL(255)

## portfolio
Field Label | Data Type | values
Customer | Lookup
End Date | Date
Investment Nature | Picklist | professional services
GTM
Capability building
R & D
Planned Budget | Currency(12, 2)
Portfolio Goals | Picklist (Multi-Select) | Customer satisfaction
Grow Business
Run Business
Transformation
Portfolio Long Description | Long Text Area(32000)
Start Date | Date
Status | Picklist | draft
active
completed
cancelled
Total Cost | Currency(12, 2)

## work request
Field Label | Data Type | values
"I need to know by" Date | Date
Customer | Lookup(Account)
Associated Portfolio | Lookup(Portfolio)
Assumptions | Long Text Area(32000)
Business Sponsor | Picklist | Accounting
HR
Operations
Other
Sales
Support
Estimated Cost Budget | Currency(12, 2)
Estimated Hours Budget | Number(12, 2)
Evaluation Date | Date
Executive Sponsor | Lookup(User)
Expected Cost Savings | Currency(12, 2)
Expected Revenue Increase | Currency(12, 2)
Goal | Picklist | Customer Satisfaction
Grow Business
Run Business
Transformation
Problem Statemen | Long Text Area(32000)
Proposed Solution | Long Text Area(32000)
Regions | Picklist (Multi-Select) | APAC
EMEA
NA
LACA
Requestor | Lookup(User)
Short Description | Text(55)
Work Request Status | Picklist | Draft
Submitted
IT Review
Procurement Review
Accepted
Rejected
Work Request Type | Picklist | Project Request
Scope Change
Enhancement Request
Infrastructure Request
Other

## project
Field Label | Data Type | values
Actual Project Delivery Date | Date
Actual Project Start Date | Date
Business Unit Sponsor | Picklist | Accounting
HR
Operations
Other
Sales
Deadline | Date
Delivered Business Asset | Picklist | Application
Human Capital
Information
Infrastructure
Operations/Services
Description | Long Text Area(5000)
Duration | Formula (Number) | deadline__c - Kickoff__c + 1
Estimated Delivery Date | Date
Estimated Start Date | Date
Expense Summary - Deprecated | Rollup from Milestone SUM(Expense)
Investment Nature | Picklist | support
implementation(Time & material)
R & D
Solution building
Implementation (Fixed Price)
Kickoff | Date
Next Project Milestone Due Date | Date
Next Project Top Milestone Due Date | Date
Number of Incomplete Milestones | Number(18, 0)
Number of Incomplete Top Milestones | Number(18, 0)
Percent Complete (Costs) | Formula (Percent)
Percent Complete (Hours) | Formula (Percent)
Portfolio | Lookup(Portfolio)
Project Manager | Lookup(Team Member)
Project Phase | Picklist | Design and Development
Draft - Phase Zero
QA
Proof of Concept
Release
Remaining (Costs) | Formula (Currency) | total_Expense_Budget__c - Total_Expense_Incurred__c
Remaining (Hours) | Formula (Number) | total_Hours_Budget__c - Total_Hours_Incurred__c
Stage | Picklist | Requirement Gathering
Design
Development
Testing
UAT
Status | Picklist | open
On Hold
In Progress
Completed
Total Blocked Task Count | Number(18, 0)
Total Complete Task Count | Number(18, 0)
Total Expense Budget | Currency(16, 2)
Total Expense Budget from Milestones | Currency(16, 2)
Total Expense Estimate | Currency(16, 2)
Total Expense Incurred | Currency(16, 2)
Total Hours Budget | Number(16, 2)
Total Hours Budget from Milestones | Number(16, 2)
Total Hours Estimate | Number(16, 2)
Total Hours Incurred | Number(16, 2)
Total Late Task Count | Number(18, 0)
Total Open Task Count | Number(18, 0)
User | Lookup(User)
Work Request1 | Lookup(Work Request)
Development & design
Quality assurance
release
|  |  | Action | Values | Default | Chart Colors | Modified By
|  |  | Edit ¦ Del ¦ Deactivate | Application |  | Assigned dynamically | ITC-PPM Dev Instance, 5/24/2016 11:36 AM
|  |  | Edit ¦ Del ¦ Deactivate | Human Capital |  | Assigned dynamically | ITC-PPM Dev Instance, 5/24/2016 11:36 AM
|  |  | Edit ¦ Del ¦ Deactivate | Information |  | Assigned dynamically | ITC-PPM Dev Instance, 5/24/2016 11:36 AM
|  |  | Edit ¦ Del ¦ Deactivate | Infrastructure |  | Assigned dynamically | ITC-PPM Dev Instance, 5/24/2016 11:36 AM
|  |  | Edit ¦ Del ¦ Deactivate | Operations/Services |  | Assigned dynamically | ITC-PPM Dev Instance, 5/24/2016 11:36 AM

## team members
Field Label | Data Type | values
Approximate Hours/Week | Formula (Number) | Estimated_Hours__c / Hours_Worked__c
Assigned Contact | Lookup(Contact)
Assignment Description | Text Area(255)
End Date | Date
Estimated Hours | Number(3, 0)
Hours Worked | Formula (Number) | ( End_Date__c - Start_Date__c ) * 24
Is Active | Checkbox
Milestone | Lookup(Milestone)
Planned Deliverables | Long Text Area(32768)
Project | Master-Detail(Project)
Requested Allocation | Percent(18, 0)
Role | Picklist | Developer
Tester
Solution Lead
Business Analyst
Individual Contributor
Project Manager
Support Specialist
Start Date | Date
Status | Picklist | Draft
Requested
Reserved
Confirmed
Canceled
User | Lookup(User)

## milestone
Field Label | Data Type | Values
Actual Expense From Sub-tasks | Currency(16, 2)
Actual Expense From Tasks | Roll-Up Summary (SUM sub Task) | Summarised Object (Task)-->SUM(Estimated Expense)
Actual Hours From Sub-tasks | Number(16, 2)
Actual Hours From Tasks | Roll-Up Summary (SUM sub Task) | Summarised Object (Task)-->SUM(Estimated Hours)
Blocked Tasks (in Milestones) | Number(18, 0)
Blocked Tasks (in Tasks) | Roll-Up Summary (COUNT Task)
Complete | Checkbox
Complete Tasks (inMilestones) | Number(18, 0)
Complete Tasks (in Tasks) | Roll-Up Summary (COUNT Task)
Deadline | Date
Description | Long Text Area(5000)
Duration | Formula (Number) | Deadline__c - Kickoff__c + 1
Kickoff | Date
Estimated Expense From Sub-Milestones | Currency(16, 2)
Estimated Hours From Sub-Taks | Number(16, 0)
Estimated Hours From Tasks | Roll-Up Summary (SUM Task)
Expense Budget from Milestones | Currency(16, 2)
Hours Budget from Milestones | Number(16, 2)
Late sub Tasks | Number(18, 0)
Late Tasks | Roll-Up Summary (COUNT Task)
Milestone Alias | Text(10) (Unique Case Insensitive)
Milestone Expense Budget | Currency(16, 2)
Milestone Hours Budget | Number(16, 2)
Open, Late & Blocked Tasks - Deprecated | Formula (Text) | IF( max( Total_Open_Tasks__c, Total_Late_Tasks__c, Total_Blocked_Tasks__c) > 0,
IMAGE("http://chart.apis.google.com/chart?chxt=y&chbh=a&chs=300x225&cht=bvg&"&
"chxr=0,0," & Text(max( Total_Open_Tasks__c, Total_Late_Tasks__c, Total_Blocked_Tasks__c)) & "&"&
"chco=eeaa66,2299bb,ee3322&chdl="&
"Open (" & TEXT(Total_Open_Tasks__c) & ")"&
"¦Late (" & TEXT(Total_Late_Tasks__c) & ")"&
"¦Blocked (" & TEXT(Total_Blocked_Tasks__c) & ")"&
"&chd=t:"& TEXT(Total_Open_Tasks__c/ max(Total_Open_Tasks__c, Total_Blocked_Tasks__c, Total_Late_Tasks__c) * 100)&"¦"& TEXT(Total_Late_Tasks__c / max(Total_Open_Tasks__c, Total_Blocked_Tasks__c, Total_Late_Tasks__c) * 100) &"¦" & TEXT(Total_Blocked_Tasks__c/ max(Total_Open_Tasks__c, Total_Blocked_Tasks__c, Total_Late_Tasks__c) * 100) , "Project Status, Open Tasks, Late Tasks & Blocked Tasks"),'')
Open sub Tasks | Number(18, 0)
Open Tasks | Roll-Up Summary (COUNT sub Task)
Open vs. Complete Tasks - Deprecated | Formula (Text) | IMAGE("http://chart.apis.google.com/chart?chco=eeaa66,2299bb&chs=300x225&cht=p&chd=t:"&Text( Total_Open_Tasks__c )&","&Text(Total_Complete_Tasks__c)&"&chdl="&
"Open%20Tasks (" & TEXT(Total_Open_Tasks__c) &")"&
"¦Complete%20Tasks (" & TEXT(Total_Complete_Tasks__c) &")"
,"Open vs. Complete Tasks")
Project | Lookup(Project)
Project Kickoff Offset | Formula (Number) | NULLVALUE(Kickoff__c - Project__r.Kickoff__c,0)
Total Actual Expense | Formula (Currency) | Actual_Expense_From_Tasks__c + Actual_Expense_From_Sub_Milestones__c
Total Actual Hours | Formula (Number) | Actual_Hours_From_Tasks__c + Actual_Hours_From_Sub_Milestones__c
Total Blocked Tasks | Formula (Number) | Blocked_Tasks_in_Tasks__c + Blocked_Tasks_in_Sub_Milestones__c | ROLLUP(COUNT(Task) where task.Blocked__c=="true"
Total Complete Tasks | Formula (Number) | Complete_Tasks_in_Tasks__c + Complete_Tasks_in_Sub_Milestones__c
Total Estimated Expense | Formula (Currency) | Estimated_Expense_From_Tasks__c + Estimated_Expense_From_Sub_Milestones__c | ROLLUP(SUM(Estimated Expense))Task
Total Estimated Hours | Formula (Number) | Estimated_Hours_From_Tasks__c + Estimated_Hours_From_Sub_Milestones__c | ROLLUP(SUM(Estimated Hours))Task
Total Expense Balance | Formula (Currency) | Total_Estimated_Expense__c - Total_Actual_Expense__c
Total Expense Budget | Formula (Currency) | Expense_Budget__c + Expense_Budget_from_Sub_Milestones__c
Total Hours Balance | Formula (Number) | otal_Estimated_Hours__c - Total_Actual_Hours__c | ROLLUP(SUM( Hours Balance))Task
Total Hours Budget | Formula (Number) | Hours_Budget__c + Hours_Budget_from_Sub_Milestones__c
Total Late Tasks | Formula (Number) | Late_Tasks_in_Tasks_2__c + Late_Tasks_in_Sub_Milestones__c | ROLLUP(SUM( Late Tasks))Task
Total Open Tasks | Formula (Number) | Open_Tasks_in_Tasks__c + Open_Tasks_in_Sub_Milestones__c

## task
Field Label | Data Type | values | Comments
Assigned To | Lookup(User)
Blocked | Checkbox
Class | Picklist | adhoc
defect
rework
Complete | Checkbox
Days Late | Number(18, 0)
Days Late Formula | Subtask-->ROLLUP-SUM(Days Late ) |  | TBD
Description | Long Text Area(5000)
Due Date | Date
Estimated Expense | Currency(16, 2)
Estimated Hours | Number(16, 2)
Expense Balance | Formula (Currency) | Estimated_Expense__c - Total_Expense__c
Hours Balance | Formula (Number) | Estimated_Hours__c - Actual_Hours__c
Import ID | Text(18)
Index Helper | Formula (Text) | Assigned_To__r.FirstName & ' ' & Assigned_To__r.LastName & ' ' & Project_Milestone__r.Project__r.Name & ' ' & Project_Milestone__r.Name & ' complete:' & IF(Complete__c, 'yes', 'no') & ' ' & Name
Last Email Received | Date/Time
Milestone | Master-Detail(Milestone)
Milestone Grandparent | Formula (Text) | if (
Project_Milestone__r.Parent_Milestone__c != null,
Project_Milestone__r.Parent_Milestone__r.Name , '')
Overall Status | Formula (Text) | if ( Complete__c == true, 'Complete',
if ( and( Days_Late_Formula__c > 0, Blocked__c ),
if(Len( Text(Task_Stage__c))>0 , 'Late & Blocked ' & Text(Task_Stage__c), 'Late & Blocked'),
if (Days_Late_Formula__c > 0,
if(Len( Text(Task_Stage__c))>0, 'Late ' & text(Task_Stage__c), 'Late'),
if(Blocked__c == true,
if(Len( Text(Task_Stage__c))>0, 'Blocked ' & text(Task_Stage__c), 'Blocked'),
if(Len( Text(Task_Stage__c))>0, 'Open ' & Text(Task_Stage__c), 'Open')
Predecessor_Task_Import_Id__c | Text(18)
Predecessor Task | Lookup(Task)
Priority | Picklist | 0
1
2
3
4
Project | Formula (Text) | IF( OR($User.UIThemeDisplayed == "Theme4d", $User.UIThemeDisplayed == "Theme4t"),
HYPERLINK('one.app?source=aloha#/sObject/' + Project_Milestone__r.Project__c + '/view',
Project_Milestone__r.Project__r.Name,
'_self'),
HYPERLINK(Project_Milestone__r.Project__c,
Project_Milestone__r.Project__r.Name,
'_self')
)
ProjectId | Formula (Text) | Project_Milestone__r.Project__c
ProjectStatus | Formula (Text) | EXT(Project_Milestone__r.Project__r.Status__c)
Reason | Text(255)
Stage | Picklist | None
New In Progress
Resolved
Closed
On-Hold Completed
Start Date | Date
Total Expense | Roll-Up Summary (SUM Expense)
Actual Hours | Roll-Up Summary (SUM(Actual hours))-Subtask
Late Tasks | checkbox | Should be auto checked once days late value is greater than 0

## sub task
Field Label | Data Type | Values
Expected Delivery Date | Date
Expected Start Date | Date
ProjectId | Formula (Text) | Task_Id__r.ProjectId__c | Pending
Stage | Picklist | New
Design
Assigned
Development
Testing
Ready to Deploy
Deployed
Status | Picklist | open
onhold
in progress
completed
Task Description | Long Text Area(32768)
Task Id | Master-Detail(Task)
Team Member | Lookup(Team Member)
User | Lookup(User)
Expense | currecny(16,2)
Due Date | Date
Days Late | Formula (Number) | Today() - Due_Date__c
Estimated Hours | Number(16,2)
Actual Hours | Number(16,2)

## issues
Field Label | Data Type | picklist values
Actual Resolution Date | Date
Assigned To | Lookup(User)
Detail | Rich Text Area(32000)
Name | Text(255)
Next Steps | Long Text Area(32768)
Planned Resolution Date | Date
Priority | Picklist | high
medium
low
Project | Master-Detail(Project)
Project Expense | Lookup(Expense)
Project Milestone | Lookup(Milestone)
Project Task | Lookup(Task)
Project Time | Lookup(Time)
Status | Picklist | Open
In-Process
Escalated
Resolved
Type | Picklist | Budget
Resource
Scope
Schedule
Quality
Risk

## risk
Field Label | Data Type | Values
Contingency Plan | Text Area(255)
Mitigation Plan | Long Text Area(32768)
Next Steps | Text Area(255)
Project | Lookup(Project)
Project Milestone | Lookup(Milestone)
Project Task | Lookup(Task)
Risk Category | Picklist | ROI / Benefits Budget Resource Scope Schedule Quality
Risk Closed Date | Date
Risk Description | Rich Text Area(32768)
Risk Impact | Picklist | High Medium Low
Risk Name | Text Area(255)
Risk Owner | Lookup(User)
Risk Probability | Picklist | High Medium Low
Risk Status | Picklist | Open In Progress Closed

## resource management
Field Label | Data Type
user name | Rich Text Area(32000)
date of joining | calender
skills | Rich Text Area(32000)
user details | Rich Text Area(32000)
total work hours planned (yearly) | Number
Total hours spent working | Number